## Slide 1: CPFM, Design and Construction
October 15, 2025
Notes: Intro of ourselves and topic
Darin and Tom

## Slide 2: Discussion Points:
Budget Constraints
Project Submission Timelines
What is a Charter
Construction Updates

## Slide 3: Effects of Campus Budget Constraints
Making Internal adjustments to increase efficiency.
  D&C is not 100% E&G funded.
  Billable hours on projects is allocated to Owners Representatives payroll.
  More engagement with internal Design and Engineering teams on projects.
  Clearer distinction between Charter process vs. Project process.
  Require User budget allocation for projects helping facilitate more efficient charter process.

## Slide 4: What to Expect with Project Submission
  Key staff
  Project Development
  Project Submission Timelines and Examples
Notes: (Tom)
Recruiting, Supporting, and Retaining a Diverse and Highly Competent Staff
Effective and Efficient Service
    Campus Service and Relationships
    Institutional Priorities
Departmental Goals

## Slide 5: Key Staff to Know
Design and Construction:
  David Cates – Design Manager and Staff Architect: dcates@uoregon.edu
    Small Project Design, Finishes and Furniture
  Bruce Budzik – Small Projects and Capital Improvement Manager: bbbudzik@uoregon.edu
    Launching of Small and Capital Repair projects
CAS and OVPRI:
  CAS: Janell Cottam – Director of Planning, Design and Facilities: janellc@uoregon.edu
  OVPRI: Amy Salmore – Assistant Director of Planning, Design and Facilities: asalmore@uoregon.edu

## Slide 6: PROJECT DEVELOPMENT
KEY PROJECT STEPS:
  Initiation from user (Project Initiation form/Call Log) cgis.uoregon.edu/CallLog; Work Control: 346-2319
  OR/PM/User define scope
  OR/PM develops charter
  Charter approval
  Design process
  Bidding and permit process
  Construction contract execution
  Construction
  Move in
  Closeout process

## Slide 7: PROJECT SUBMISSION TIMELINES: Steps 1 through 7
<$25K 10-14 weeks to start construction
$25K-$50K 12-20 weeks to start construction
$50K-$100K 14-24 weeks to start construction
$100K-$1M 24-32 weeks to start construction

## Slide 8: What is in the Charter?
Document to align user request and project requirements.
Documents leadership unit, requesting department, and budget authority for project.
Documents Design and Construction project contacts.
Summarizes the scope of the project with required elements, optional elements, and constraints.
Summarizes assumptions, risks and exclusions in the project scope.
Provides a budget opinion range, funding requirements and overall duration.
Notes: (Darin)
CPFM Sub Org.
Staffing
  33 current staff (8 unfilled)
    15 OAs
    18 Classified
Organizational Structure
  Academic/Auxiliary
  Science and Research
  Small Project/Capital Improvement
  Engineering
  Design
  Business Operations

## Slide 9: What is not in the Charter?
Common Misconceptions:
Detailed line-item cost of the project.
Bid or fixed price.
Multiple design options, or, a la cart menu.
Notes: Stabilizing Organizational Structure and Roles Within CPFM (Darin)
Improving Campus Relationships (Darin)
  CAS Administration
  OVPRI
Process Stabilization (Tom)

## Slide 10: Active Project Highlights
Under Construction
Friendly Hall Deferred Maintenance
Next Gen Housing
Hamilton Demo
College of Design Acoustic Testing Chamber
In-Design
Knight Library Exterior Restoration Ph III
Elevator Modernizations
Roof replacements
Child Behavioral Health:DD, Portland Campus
https://cpfm.uoregon.edu/construction-map

## Slide 11: Questions?